## Slide 1: Stephen Ambrose GOES-R Data Operations Manager (DOM) OSPO/SPSD
March 12, 2013
GOES-R Ground Segment Project
Data Operations Support Team
System Validation Activities
Brief to NWS-NESDIS/SPSD Quarterly Meeting

## Slide 2: The GOES-R System-Operational View
Data and Products
Suitland, MD
Fairmont, WV
Enterprise Management
Mission
Management
Product Generation
L2+
Data and Products
Product Distribution
LAN
NSOF
RBU
LAN
MM
EM
PG (L0, L1b, L2+ GLM, GRB, KPP)
PD
MM: Mission Management
EM: Enterprise Management
PG: Product Generation
PD: Product Distribution
HRIT/EMWIN, GRB
SARSAT
GEOLUT
BEACONS
DCS
DRGS
Data Collection Platforms (DCP)
MM
EM
PG
PD
Wallops, VA
75o
WAN
137o
Product Dist. & Access (PDA) (GOES-R Access Subsystem- GAS)
User Community
Operate Satellites
Operate Ground Seg
Maintain
Ground Seg
Produce Products
Data and Products
LAN
WCDAS
DCPC
DCPR
DCS
L1b,
L2+ GLM, GRB, KPP
L0,

## Slide 3: DOM/DOST “Mission”
DOM = Data Operations Manager
DOST = Data Operations Support Team
Prepare OSPO to operate the Core GS Data Processing and Distribution System (DPDS)
Validate that the Core GS “DPDS” is Mission Capable and Mission Ready
Facilitate Consumer System Readiness for GOES-R Data Operations
Accomplished by
  Procedure and CONOP Development
  Prototypes and Exercises
  Facilitation of Test Data
  Planning and Execution of two Pre-Launch “Data Operations Tests” (DOT)
  Support for Post-Launch Tests

## Slide 4: Data Operations Tests
Two Pre-Launch Validation Opportunities
  DOT-1: Directly following GS Release One
  DOT-2: Directly after GS is complete (Release 1a and Release 2)
One month sustained data operations
  Continuous “Forecast Based” Level 1B
  Interrupts for special test cases
Facilitate readiness testing of downstream users

## Slide 5: Data Flow through the GOES-R System
Direct Broadcast
Community
NOAAPort
Community
Climate, Research, and Academia
NWS
Forecast Offices
Operational
User Community
NOAA Centers, DOD, NCEP, International Partners
WCDAS
NSOF
RBU
C
C
C
P
D
A
P
D
P
G
M
M
P
D
P
G
M
M
P
D
P
G
M
M
TNCF
BNCF
ANCF
NCDC
NGDC
Ancillary
Sources
Validation Responsibility
Consumer System Readiness Support

## Slide 6: Normal DOT Data Flow
NOAAPort
Community
Climate, Research, and Academia
NWS
Forecast Offices
Operational
User Community
NOAA Centers, DOD, NCEP, International Partners
WCDAS
NSOF
RBU
C
C
C
P
D
A
P
D
P
G
M
M
P
D
P
G
M
M
P
D
P
G
M
M
TNCF
BNCF
ANCF
NCDC
NGDC
Ancillary
Sources
Validation Responsibility
Consumer System Readiness Support
Forecast
Based
Fixed Grid
L1b
Forecast
Based
Fixed Grid
L1b
Pretend
Sat
Direct Broadcast
Community
*

## Slide 7: Canned “End-to-End” Test during DOT-1
NOAAPort
Community
Climate, Research, and Academia
NWS
Forecast Offices
Operational
User Community
NOAA Centers, DOD, NCEP, International Partners
WCDAS
NSOF
RBU
C
C
C
P
D
A
P
D
P
G
M
M
P
D
P
G
M
M
P
D
P
G
M
M
TNCF
BNCF
ANCF
NCDC
NGDC
Ancillary
Sources
Validation Responsibility
Consumer System Readiness Support
Simulated
CCSDS
Packet Stream
Simulated
CCSDS
Packet Stream
Pretend
Sat

## Slide 8: DOT Planning
V
MRD
Validation
Objectives
Test
Objectives
Test
Design
Development:
Test Procedures
Data and Component Simulators
Analysis Tools
Approaching with Systems Engineering Discipline
Test Execution and Analysis
DOT-1
DOT-2
Validation Assessment
GRD

## Slide 9: Left Side of the V – Validation Objectives
Validation Objectives
  Validation is not a repeat of Verification
    Incorporate the People and Mission aspect
    Run in a “dirty” environment
    Interact with the real world
  Validation Objectives are to Validation
    …as Requirements are to Verification
    Decompose them like requirements
    Account for them like requirements
    But…
    V.O.s can be subjective, not necessarily pass/fail
    Use V.O.s to establish shared expectations with Stakeholders

## Slide 10
Artwork by NWS/AWIPS, courtesy Brian Gockel

## Slide 11: DOST Project Overview
Phase One – Project Definition
  Completed
Phase Two – Preliminary Design
  Dec 2012 – Apr 2013
Phase Three – Detail Design
  Apr 2013 – Oct 2013
Phase Four – Implementation
  Nov 2013 – Apr 2014
Phase Five – Execution of Pre-Launch Testing
  May 2014- Apr 2015
Phase Six – Execution of Post-Launch Testing

## Slide 12: Phase Two Overview
Validation Objectives Review
Validation Objective Decomposition
Development of Ops Procedure List
Preparation of Validation Plan version 1
Coordination of External Validation Objectives Development

## Slide 13: Phase Three Overview
Validation Preliminary Design Review
Test Designs
Data Set and Simulator Specifications
Analysis Tool Specifications
Oversight of Ops Procedure Development
Preparation of Validation Plan rev 2
Coordination with External Validation Test Developments

## Slide 14: Phase Four Overview
Validation Critical Design Review
Data Set and Generator Implementation
Tools Implementation
Test Procedure Development
Ops Procedure Evaluation and Development
Early Opportunity Testing

## Slide 15: Phase Five Overview
DOT-1 Test Readiness Review
Execution of DOT-1
DOT-1 Analysis and Reporting
DOT-2 Test Readiness Review
Execution of DOT-2
DOT-2 Analysis and Reporting

## Slide 16: DOST Top Level Schedule
December 31, 2012

## Slide 17: Validation Testing Dependencies
January 31, 2013

## Slide 18: Summary
DOM – Data Operations Manager
DOST – Data Operations Support Team
DOTS – Two One-Month Pre-Launch Shakedown Cruises
Focus: System Validation/Readiness of Data Processing & Distribution
DOVOs – Data Ops Validation Objectives
EDOVOs – External Stakeholder Data Ops Validation Objectives
Not “Re-Verification”
Not “Product Science Validation”